## Intro
Task Managment Tracker
Project Overview
This Excel dashboard tracks task status, team workload, owner-wise progress, and overdue work to support project management decision-making. It provides visibility on task completion, pending work, and work distribution across different departments and team members.
The dashboard enables quick monitoring of project progress, helping managers identify bottlenecks, overdue work, and productivity trends.
Business Objectives
Track progress of all tasks (Completed, In Progress, Not Started).
Monitor owner-wise task distribution & responsibility.
Analyze work allocation across teams/departments.
Identify overdue & delayed tasks to take action.
Build an interactive Excel dashboard for real-time tracking.
Support project planning & resource optimization.
KPIs Measured
KPI Why It Matters
Total Tasks Shows overall project scope.
Completed Tasks Measures progress & success rate.
in-Progress Tasks indicates ongoing workload.
Not Started Tasks Highlights pending action items.
Owner-wise Task Count Helps assign responsibilities.
Team-wise Task Count Shows department workload.
Overdue Tasks Flags critical delays.
Data Understanding
Dataset includes:
Task Status (Completed / In Progress / Not Started)
Owners responsible
Team allocation (Finance, HR, Strategy, Marketing…)
Overdue counts
Total task summary
This structure enables clear visibility of project progress & resource allocation.
Data Cleaning & Structuring
✔ Removed blanks & merged cells ✔ Cleaned headers for KPI reading ✔ Created structured tables for pivot use ✔ Converted data into Excel Table format ✔ Added helper columns for dashboard calculations
Data Analysis & Insights
Owner-Wise Analysis
Sarah Johnson completed 6 tasks
David Kim handled 3 tasks
Some owners handled only 1 task → can take more work
Workload is uneven – potential for redistribution
Team-Level Insights
Strategy & HR teams have highest number of active tasks
Marketing has only 1 task → underutilized
Finance is moderately loaded
Helps decide hiring / internal shifts
Overdue Tasks
8 tasks overdue → need urgent follow-up
Potential risk to project timeline
Dashboard highlights overdue items using conditional formatting
Skills Used
Excel Skills
Pivot Tables & Charts
SUMIFS / COUNTIFS
Data Cleaning & Table formatting
Conditional Formatting
Dashboard Visualization
Slicers & Filtering
KPI Card Creation
Analytics Skills
Resource Allocation Analysis
Team Workload Optimization
Task Performance Tracking
Bottleneck Identification
Risk Management (overdue tasks)
Soft Skills
Project coordination
Insight storytelling
Decision support
Stakeholder communication

## Dashboard
Task ID | Task Name | Team | Task Owner | Start Date | Due Date | Task Duration | Status | Overdue? | Comments
T001 | Prepare Q4 Financial Report | Finance | Sarah Johnson | 2025-09-02 | 2025-09-20 | 18 | Completed | FALSE | Submitted to CFO for review.
T002 | Conduct Market Research | Strategy | Sarah Johnson | 2025-09-05 | 2025-09-25 | 20 | Completed | FALSE | Draft findings ready; awaiting survey data.
T003 | Redesign Website Homepage | Strategy | David Kim | 2025-07-10 | 2025-08-05 | 26 | In Progress | TRUE | Wireframes approved; development in progress.
T004 | Update Sales Forecast for FY2026 | Finance | Sarah Johnson | 2025-09-12 | 2025-09-30 | 18 | Completed | FALSE | Final version shared with Sales Director.
T005 | Implement CRM Upgrade | Strategy | James Miller | 2025-09-15 | 2025-10-10 | 25 | In Progress | TRUE | Vendor confirmed delivery timeline.
T006 | Plan Annual Company Retreat | HR | David Kim | 2025-09-18 | 2025-10-15 | 27 | In Progress | TRUE | Venue options being shortlisted.
T007 | Review Legal for Contracts | HR | Alex Chen | 2025-08-20 | 2025-08-27 | 7 | Not Started | TRUE | Updated contracts aligned with new regulation.
T008 | Launch Social Media Campaign | Marketing | Alex Chen | 2025-09-22 | 2025-10-12 | 20 | In Progress | TRUE | Initial creatives approved, campaign scheduled.
T009 | Recruit New Data Analyst | HR | Sarah Johnson | 2025-09-23 | 2025-10-20 | 27 | Completed | FALSE | First round of interviews completed.
T010 | Conduct Employee Survey | HR | Sarah Johnson | 2025-09-24 | 2025-10-05 | 11 | In Progress | TRUE | Survey questions finalized.
T011 | Prepare Investor Presentation | Finance | David Kim | 2025-09-25 | 2025-10-02 | 7 | Completed | FALSE | Draft slides ready; awaiting financial highlights.
T012 | Upgrade Infrastructure | Strategy | Sarah Johnson | 2025-09-26 | 2025-10-30 | 34 | Completed | FALSE | External consultant engagement pending.
T013 | Evaluate Vendor Proposals for Logistics | Strategy | Emily Davis | 2025-09-27 | 2025-10-07 | 10 | In Progress | TRUE | Three proposals shortlisted for management review.
T014 | Draft Q1 Marketing Strategy | Strategy | Emily Davis | 2025-09-28 | 2025-10-18 | 20 | Completed | FALSE | Kick-off meeting scheduled next week.
T015 | Audit Internal Expense Reports | Finance | Emily Davis | 2025-09-29 | 2025-10-04 | 5 | Not Started | TRUE | Waiting for submission of all departmental reports.
Formulas:
Overdue? = AND(([Status]<>"Completed"),([Due Date]<TODAY()))
Task Managment Tracker
Completed
7
Not Started
2
In Progress
6
Total Tasks
15
Overdue Tasks
8

## Support Sheet
Status | Count | Owners | Count | Team | Count | Overdue
Completed | 7 | Sarah Johnson | 6 | Finance | 4 | 8
In Progress | 6 | David Kim | 3 | Strategy | 6
Not Started | 2 | James Miller | 1 | HR | 4
Total | 15 | Alex Chen | 2 | Marketing | 1
|  | Emily Davis | 3